## スケジュール
API
クリエイト
No | タスク | 担当者 | time axis 2022-10-01 to 2022-11-30
1 | 新規登録 | bar: 2022-10-03
2 | ログイン | bar: 2022-10-05
3 | プロフィール | bar: 2022-10-07
4 | 共通ヘッダー | bar: 2022-10-11
5 | ムービー一覧（ホーム） | bar: 2022-10-13 to 2022-10-14
6 | ムービー詳細 | bar: 2022-10-19 to 2022-10-20
7 | 共通フッター | bar: 2022-10-25
8 | ムービー履歴 | bar: 2022-10-26
9 | ムービー作成 | bar: 2022-10-28; 2022-10-31
10 | ムービー一覧 | bar: 2022-11-03 to 2022-11-04
11 | ムービー履歴 | bar: 2022-11-08
12 | ユーザー一覧 | bar: 2022-11-10
13 | テスト | bar: 2022-11-14 to 2022-11-18

## Schedule
API
Create
FOR USER
No | Task | Team Members | time axis 2022-10-01 to 2022-11-30
1 | Database CRUD | AKM, THIRI, EIZIN
2 | UIUX | TZH, THIRI
3 | API | TZH,
2 | Register | TZH, AKM, AWYH | bar: 2022-10-03
3 | Login | TZH, AKM | bar: 2022-10-05
4 | Profile | TZH, AKM, THIRI | bar: 2022-10-07
5 | Navigation Bar (View : search, noti) | TZH, AKM | bar: 2022-10-11
6 | Post/Ads List (View) | TZH, AKM | bar: 2022-10-13 to 2022-10-14
7 | Detail Post(View Posts : Interest, Favourite) | EIZIN, THIRI | bar: 2022-10-19 to 2022-10-20
8 | Subscribe | EIZIN, THIRI | bar: 2022-10-25
9 | Create Post(Posts) | bar: 2022-10-26
10 | Create Ads(Ads) | bar: 2022-10-28; 2022-10-31
11 | Post Noti | bar: 2022-11-03 to 2022-11-04
12 | Footer | bar: 2022-11-08

## Schedule 2
API
Create
FOR USER
No | Task | Team Members | time axis 2022-10-01 to 2022-11-30
1 | Database CRUD | All Members
2 | UIUX | TZH,
3 | API | TZH
2 | Registration | AKM | bar: 2022-10-03
3 | Subscribe | THIRI | bar: 2022-10-05
4 | Creation(CRUD - Ads) | YMT | bar: 2022-10-07
5 | Creation(CRUD - Post) | EIZIN | bar: 2022-10-11
6 | Post Views(Interest/ Favourite) | AWYH | bar: 2022-10-13 to 2022-10-14
EIZIN, THIRI | bar: 2022-10-25